## Sheet1
Doctor Dashboard Task Sheet
Date | Slide | Description | Front End Design |  | Front End Logic |  | Backend Service |  | Email |  | QA/Testing
|  |  | Task | Time Taken (In Hrs.) | Task | Time Taken (In Hrs.) | Task | Time Taken (In Hrs.) | Task | Time Taken (In Hrs.) | Task | Time Taken (In Hrs.)
2018-11-01 | 1 | Post Sign In | To Merge the existing Design | 2 |  |  | Doctor to child relation to be added | 1 |  |  | Check all the design & Functionality | 1
2018-11-01 | 2 | Selecting Appointment | To Merge the existing Design | [7 empty] | Check all the design & Functionality | 1
2018-11-01 | 3 | Display kids as per appointment | To Merge the existing Design |  |  |  | To pull all data from Visit list | 1 |  |  | Check all the design & Functionality | 1
2018-11-01 | 4 | Dashboard Display | To split into 3 section
2018-11-01 |  |  | 1. Child Data | 1 | To send the child id | 1 | To pull all data for the particular child | 1 |  |  | Check all the design & Functionality | 1
2018-11-02 |  |  | 2. Parent Questionaire |  | To send the child id | 1
2018-11-02 |  |  |  |  | Display Quick View as default | 1 | To pull all data for the particular child First 3 | 1 |  |  | Check all the design & Functionality | 1
2018-11-02 |  |  |  |  | Enable Detailed view | 1 | To pull all data for the particular child | 1 |  |  | Check all the design & Functionality | 1
2018-11-02 |  |  |  |  | Enable to change Core Framework | 1 | To pull data as per the selection | 1 |  |  | Check all the design & Functionality | 1
|  |  | 3. Child Development parameters |  | To send the child id
2018-11-03 |  |  |  |  | To display subject wise report | 1 | To pull consolidated report from the last visit average by subject and grouped by core and subject | 3 |  |  | Check all the design & Functionality | 2
2018-11-08 |  |  |  |  | Drill down of subject | 1 | To pull consolidated report and average by games for the specific subject and grouped by core and games | 2 |  |  | Check all the design & Functionality | 2
2018-11-09 |  |  |  |  | Drill down of games | 1 | To pull report by games for the specific game |  |  |  | Check all the design & Functionality | 2
Total Hours |  | 35 |  | 3 |  | 8 |  | 11 |  | 0 |  | 13
Total Days |  | 4.375