## Front End
Work Flow For Milestone Engineering - Daily Task List For Front End
S/N | Date | Description | Front End Design |  |  | Front End Logic And Development |  |  | QA/Testing
|  |  | Task | Allocated Time (In Hrs.) | Buffer Time (In Hrs.) | Task | Allocated Time (In Hrs.) | Buffer Time (In Hrs.) | Task | Time Taken (In Hrs.)
| 2020-03-03 | Game Excel Upload | Start And End Date | 30 min | 30 min | Validation | 30 min | 30 min
| 2020-03-03 | Game Excel Upload | Show the date in excel formet | 2 | 1 | Get the data from api and show the data | 1 | 1 | 05-03-2020 Second half
| 2020-03-03 | Weekly Task Status | Add New Screen And show the all team with start and end date | 1 | 1 | Get the data from api and link the team wise | 1 | 30 min
| 2020-03-03 | Create Game | Add disable color and add title with date | 30 min | 30 min
| 2020-03-04 | Team wise show the details | To Show the list in task details | 3 | 1 | Get the data from api And Show the details. Check the status and set color | 1 | 30 min
| 2020-03-04 | Game Admin Page | Step: 1 Add new screen and show all team members weekly task details | 2 | 1 | Get the data from api and show the data | 1 | 30 min
| 2020-03-05 | Game Admin Page | Step: 2 To Show the list in task details for member | 1 | 1 | Get the data from api and show the data | 1 | 1
| 2020-03-05 | Game Admin Page | Step 3: Assign milestone activity to the team member | 3 | 1 | Validation and dynamic form | 30 min | 30 min

## Bakend
Work Flow For Milestone Engineering - Daily Task List For Backend
S/N | Date | Description | Backend Service |  |  | QA/Testing
|  |  | Task | Allocated Time (In Hrs.) | Buffer Time (In Hrs.) | Task | Allocated Time (In Hrs.)
| 2020-03-03 | Add start date and end date | To add two field in daily game schedule | 10 min | 10 min | 05-03-2020 second half
| 2020-03-03 | Get the excel sheet form | Get the data from daily game schedule table based on month week grade | 2 | 1
| 2020-03-03 | Add work flow team | Add field name (id,team_name) | 30 min | 30 min
| 2020-03-03 | Get the team details with work flow date | Get the data from daily game schedule table based on current date | 1 | 1
| 2020-03-03 | Get the game task | Get the data from daily game schedule table based on start and end date with user details also | 1 | 1
| 2020-03-04 | Get the team members | Get the data from user table based on user type | 30 min | 30 min
| 2020-03-04 | Get the weekly task | Get the data from daily game schedule based on user and start and end date | 1 | 1
| 2020-03-04 | Assign milestone activity | Add the dtetails in allocation game table with start and end date | 1 | 1

## Game Template
Task List For Game Creation
S/N | Date | Description | Template Creat |  | QA/Testing
|  |  | Task | Time Taken (In Hrs.) | Task | Time Taken (In Hrs.)

## SQL
Task List For SQL
S/N | Date | Description | Task | QA/Testing

## Local server
Task List For Local Server
S/N | Date | Description | Task | Time

## AWS
Task List For AWS
S/N | Date | Description | Task | Time

## School Work
Task List For School Server
S/N | Date | Description | Task | Time