## Sheet1
Funtonality Name | Sub Functions | Written By | Completion status | QA Status
Admin Dash Board | UI and JS | Mohan | Yes | Completed
| User Count Service | Guna | Yes | Completed
| User Count Drill Down Service | Guna | Yes | Completed
| Transaction Service | Sreekanth | Yes | Completed
| Transaction Drill Down Service | Sreekanth | Yes | Completed
| Work Progress Service | Sreekanth | Yes | Completed
| Target Achievement Service | Sreekanth | Yes | Completed
Agri Dashboard | UI and JS | Mohan | Yes | Completed
| User Count Service | Sreekanth | Yes | Completed
| User Count Drill Down Service | Sreekanth | Yes | Completed
| Transaction Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Transaction Drill Down Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Work Progress Service | Sreekanth | Yes | Completed
| Target Achievement Service | Sreekanth | Yes | Completed
TNAU Dashboard | UI and JS | Mohan | Yes | Completed
| User Count Service | Sreekanth | Yes | Completed
| User Count Drill Down Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Transaction Service | Sreekanth | Yes | Completed
| Transaction Drill Down Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Work Progress Service | Sreekanth | Yes | Completed
| Target Achievement Service | Sreekanth | Yes | Completed
Horticulture Dashboard | UI and JS | Mohan | Yes | Completed
| User Count Service | Sreekanth | Yes | Completed
| User Count Drill Down Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Transaction Service | Sreekanth | Yes | Completed
| Transaction Drill Down Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Work Progress Service | Sreekanth | Yes | Completed
| Target Achievement Service | Sreekanth | Yes | Completed
AED Dashboard | UI and JS | Mohan | Yes | Completed
| User Count Service | Sreekanth | Yes | Completed
| User Count Drill Down Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Transaction Service | Sreekanth | Yes | Completed
| Transaction Drill Down Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Work Progress Service | Sreekanth | Yes | Completed
| Target Achievement Service | Sreekanth | Yes | Completed
Animal Husbandary Dashboard | UI and JS | Mohan & Jamseer | Yes | Completed
| User Count Service | Sreekanth | Yes | Completed
| User Count Drill Down Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Transaction Service | Sreekanth | Yes | Completed
| Transaction Drill Down Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Work Progress Service | Sreekanth | Yes | Completed
| Target Achievement Service | Sreekanth | Yes | Completed
WRD Dashboard | UI and JS | Mohan & Jamseer | Yes | Completed
| User Count Service | Sreekanth | Yes | Completed
| User Count Drill Down Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Transaction Service | Sreekanth | Yes | Completed
| Transaction Drill Down Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Work Progress Service | Sreekanth | Yes | Completed
| Target Achievement Service | Sreekanth | Yes | Completed
Marketing Dashboard | UI and JS | Mohan & Jamseer | Yes | Completed
| User Count Service | Sreekanth | Yes | Completed
| User Count Drill Down Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Transaction Service | Sreekanth | Yes | Completed
| Transaction Drill Down Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Work Progress Service | Sreekanth | Yes | Completed
| Target Achievement Service | Sreekanth | Yes | Completed
Fisheries Dashboard | UI and JS | Mohan & Jamseer | Yes | Completed
| User Count Service | Sreekanth | Yes | Completed
| User Count Drill Down Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Transaction Service | Sreekanth | Yes | Completed
| Transaction Drill Down Service | Sreekanth | Yes | Will be updated on 17.8.2020
| Work Progress Service | Sreekanth | Yes | Completed
| Target Achievement Service | Sreekanth | Yes | Completed