## 13-03-2020
Component Based Game Create Application - Daily Task list
Teme Name
| Front End | Description | Task | Allocated Time (In Hrs.) | Buffer Time (In Hrs.)
|  | Game Create Page | To add a new component for game creation with routing | 2 | 1
|  | Data Form in Angular | Create a new ngForm for data send with valitation | 4 | 1
|  | Valitation | Valitation and formcontrol | 2 | 1
| Game Teme | Game Component With Audio and Image | To tack list for audio and image and game component based on games | Full Day
| SQL | Game Component Table | To create game component base on component details | 2 | 30min
|  | Image and Audio Table | To create image and audio table | 1 | 30min
|  | Component Map | To create component map with image and audio | 3 | 30min
|  | Testing | To check all filde and value | 30min
|  | Testing | To check all filde and value | 30min

## 16-03-2020
Component Based Game Create Application - Daily Task list
Teme Name
| Front End | Description | Task | Allocated Time (In Hrs.) | Buffer Time (In Hrs.)
|  | Image Audio Add | To check image and audio based on game component to add upload list in both | 3 | 1
|  | Logic And Development | Check the image and audio in backend to add one by one in upload section | 1 | 1
| Bank End | Get game component list | Get the game component list and sent in to api | 1 | 1
|  | Create game folder | Get the input data and create a game folder based on data | 2 | 1
|  | Copy image and audio | To copy the file in game folder | 2 | 1
| Game Teme | Set Component Flow and Data send API | Check the all component flow and data send and to get replay count | 1day

## 17-03-2020
Component Based Game Create Application - Daily Task list
Teme Name
| Front End | Description | Task | Allocated Time (In Hrs.) | Buffer Time (In Hrs.)
|  | Game Flow section | Add a new section for set game work flow | 3 | 1
|  | Game Play | Add a game play section for testion | 1 | 1
|  | Logic And Development | Set the game flow based on select component list | 2 | 1
| Back End | Code generator | Create a code and seve ther file in game folder | 1 day
| Game Teme | Set Component Flow and Data send API | Check the all component flow and data send and to get replay count | 1day

## 18-03-2020
Component Based Game Create Application - Daily Task list
Teme Name
| Front End | Description | Task | Allocated Time (In Hrs.) | Buffer Time (In Hrs.)
|  | QA | To test to all function in front end | 3 | 1
| Back End | Create a game | To create a new game base on game components | 3 | 1
| Game Teme | Set Component Flow and Data send API | Check the all component flow and data send and to get replay count | 1day
| SQL | Insert Data | To insert component data in the table | 4 | 1
|  | Insert Image and Audio Data | To insert image and audio data in the table | 4 | 1

## 19-03-2020
Component Based Game Create Application - Daily Task list
Teme Name
|  | Description | Task | Allocated Time (In Hrs.) | Buffer Time (In Hrs.)
| Game Teme | Set Component Flow and Data send API | Check the all component flow and data send and to get replay count | 1day
| SQL | Component Map | To create component map with image and audio | 3 | 1

## 20-03-2020
Component Based Game Create Application - Daily Task list
Teme Name
|  | Description | Task | Allocated Time (In Hrs.) | Buffer Time (In Hrs.)
| Game Teme | Set Component Flow and Data send API | Check the all component flow and data send and to get replay count | 1day

## 23-03-2020
Component Based Game Create Application - Daily Task list
Teme Name
|  | Description | Task | Allocated Time (In Hrs.) | Buffer Time (In Hrs.)
| Game Teme | Set Component Flow and Data send API | Check the all component flow and data send and to get replay count | 1day

## 24-03-2020
Component Based Game Create Application - Daily Task list
Teme Name
|  | Description | Task | Allocated Time (In Hrs.) | Buffer Time (In Hrs.)
| Game Teme | Final Qu For All Component | To test all component | Full Day

## 26-03-2020
Component Based Game Create Application - Daily Task list
Teme Name
|  | Description | Task | Allocated Time (In Hrs.) | Buffer Time (In Hrs.)
| QA | Final Qu For Application Full Flow | To test and check flow and changing | Full Day